# Company Name

# Job Process Outline

## The Job Process begins when a customer signs the proposal

# Sales Estimator

## If Customer hands signed proposal and contract to salesman, submit the following to the Office:

### Signed Proposal

### Signed Contract

### Customer Deposit

### Work Order with “Promised to Customer Notes” included.

### Job Estimate Spreadsheet

## If Customer will return signed proposal and contract by mail, submit the following to the Office:

### Work Order with “Promised to Customer” notes included.

### Job Estimate Spreadsheet

## Within 2 days of job completion:

### Call customer to follow up on Customer Satisfaction

### Discuss one year inspection with customer

### Schedule date to re-contact customer in CRM (Customer Relationship Management software: ACT, Outlook, etc)

# Office

## Upon receipt of signed proposal, contract and deposit:

### Create QuickBooks File, assigning a file name using standard naming convention

### Enter Deposit in QuickBooks from customer check

### Enter Job Estimate in QuickBooks from Work Order

### Start a Job Process Checklist (duplicate, one copy for office folder, one for field folder)

### Schedule the job in Job Calendar

## Within 2 days of receipt of signed proposal:

### Complete standard Customer Contact Letter (or email) with schedule and payment amounts.  Obtain schedule dates from Job Calendar and payment amounts from Contract.

### Send new customer letter (or email) along with customer to do list and payment schedule and RRP info if needed

### Assemble the Field Folder with the following:

#### Customer Communication Log

#### Color Schedule

#### Change Order Forms (2)

#### Customer Satisfaction Feedback Form with self addressed stamped envelope

#### Pre Job Check List

#### Post Job Check List

#### Contact Log (stapled to outside right front)

#### Copy of Work Order

#### Copy of Proposal

#### Copy of Customer Contact Letter

#### Copy of Job Process Checklist

### Assemble the following and clip to front of Field Folder

#### Job Process Check List

#### Copy of Proposal

#### Copy of Contract

#### Job Estimate Spreadsheet

### Forward Field Folder with Attachments to Production Manager

### Assemble the Office Folder with the following:

#### Job Process Checklist

#### Original signed Contract

#### Original signed Proposal

#### Copy of Customer Contact Letter

### File Pre-Lien if needed

## While Job is in Progress:

### Invoice Change Orders in needed

### Collect Material Invoices

### Receive and process progress payments

## When Job is complete:

### Receive and process final payment

### Receive and file the following and add to Office File

### Completed Pre Job Check List

### Completed Post Job Check List

### Completed Color Schedule

### Notify owner of delinquent payments

## Within one week of Job completion:

### Enter Customer Satisfaction Letter information into Customer Satisfaction database

### Send Thank you gift and note

### Complete Job Cost Analysis

### Follow up on any open items

### Re-file completed job file

## Second week of each month:

### Compile job cost data for all jobs completed in prior month

### Print Job Cost Summaries & Charts for the following:

#### Owner

#### Production Mgr.

#### Individual Foreman

#### Office Manager

# Production Manager

## 2 weeks before scheduled job:

### Contact customer and schedule walk through

## At walk through appointment:

### Complete Color Confirmation

### Review Customer “To Do” List and Payment Schedule with customer

## One week before scheduled job

### Order Special Equipment

### Contact customer to confirm final job schedule

### Forward Field Folder to Foreman

## Day of Job Completion

### Contact customer in person or by phone to answer questions or concerns

### Schedule return touch-ups if required

# Foreman

## One week before job start

### Review Field Folder

### Order Paint and supplies

## First Day of Job

### Conduct Pre Job walk-through

### Confirm Colors

### Complete Pre Job Check List

## While Job is in Progress:

### Collect progress payments according to schedule

### Report hours works and job progress daily (via phone, fax or email)

### Clean up Job site daily, as appropriate

### Submit change orders with customer approval to office as required

## At Job completion:

### Conduct Post Job Walk Through

### Complete Post Job Check List

### Thank the Customer for using our company

### Return Field Folder to Office

### Return Special Equipment to provider

### Inform Production Manager of Return touch-ups if required.

# Text boxes

S

T

A

ND

A

R

D

SPEC

I

F

I

C